## Sheet1
Case # | Case Type | Application | Module / Project | Subject | Status | Owner | Created By | SD User | QA User | BA User | Approver | Severity | Priority | Customers | QA Effort Estimate (hrs) | Effort Estimate (hrs) | QA Release Date | UAT Release Date | Effort Actual (hrs) | Sprint | Short Note | Tags | Created Date | Updated Date | JIRA | Age Day(s) | Resolution Time | Rank
15098 | Enhancement | iPath | Cases | Change assignment of automated Termination Billing Cases to Jennine | In UAT | Katie Terascavage | Anilbrahmanapally Kumar | Anandani Tiwari | Santosh Poloju | Katie Terascavage | Katie Terascavage | Major |  |  | 0.3 | 2 |  | 2024-10-23 12:30 | 1 | Sprint 24.7 |  |  | 2024-10-15 10:28 | 2024-10-23 10:39 |  | 11
14430 | Enhancement | iPath | Orders | for New Add Order drafts that are sent to the PM, need the below field updated on cable and fiber b... | In UAT | Bhanu Anukonda | Michelle Faamausili | Vishnuvardhan Minampalli | Santosh Poloju | Bhanu Anukonda | Stephanie Simonds | Major |  |  | 10 | 4 | 2024-10-21 12:30 | 2024-10-16 12:30 | 2 | Sprint 24.7 |  |  | 2024-08-16 00:59 | 2024-10-16 15:21 |  | 71 |  | 1
14057 | Enhancement | Expense Management | Managed Pay | Managed Pay Aging View | In UAT | Adam Shawley | Adam Shawley | Suresh Jakka | Santosh Poloju | Adam Shawley | Adam Shawley | Major |  |  | 18 | 48 | 2024-10-21 12:30 | 2024-10-23 12:30 |  | Sprint 24.7 |  |  | 2024-07-17 21:10 | 2024-10-23 12:18 |  | 14 |  | 1
13450 | Enhancement | iPath | Cases | Add Direct Link to iPath Sales Case in Email Notification | In UAT | Katie Terascavage | Sameer Hilal | Anandani Tiwari | Santosh Poloju | Katie Terascavage | Katie Terascavage | Major |  |  | 6 | 1 | 2024-10-21 12:30 | 2024-10-18 12:30 | 1 | Sprint 24.7 |  |  | 2024-05-24 03:45 | 2024-10-18 11:29 |  | 12 |  | 12
13436 | Enhancement | vManager | AP | Change To AP Posting Process On QuantumShift Mobile Invoices | In UAT | Adam Shawley | Adam Shawley | Yugandhar Vadisela | Santosh Poloju | Adam Shawley | Bhanu Anukonda | Major |  |  | 42 | 80 | 2024-10-21 12:30 | 2024-10-25 12:30 | 60 | Sprint 24.7 |  |  | 2024-05-23 22:18 | 2024-10-25 12:10 |  | 19 |  | 4
13350 | Enhancement | vManager | Analytics | Add SLA report in vManager | In UAT | Bhanu Anukonda | Jennine Sison | Suresh Jakka | Santosh Poloju | Bhanu Anukonda | Bhanu Anukonda | Major |  |  |  | 3 |  | 2024-10-16 12:30 | 2.3 | Sprint 24.7 |  |  | 2024-05-16 21:04 | 2024-10-16 15:34 |  | 57
9960 | Enhancement | iPath | Projects | QSCARE - Network Reterm Automation | In UAT | Josh Kramer | Jennifer Williamson | Durga Bhavani | Santosh Poloju | Josh Kramer | Stephanie Simonds | Major |  |  | 60 | 121 | 2024-09-30 12:30 | 2024-09-30 12:30 | 121 | Sprint 24.7 |  | OpsPriority | 2023-10-04 00:03 | 2024-10-04 00:09 |  | 80 |  | 1
15099 | Enhancement | iPath | Software Cases | Remove vCom GPT Chat from Software Cases | Waiting to be Released | Srikanth Palepu | Nagasai Mudara | Lokesh Gogineni | Santosh Poloju | Bhanu Anukonda | Bhanu Anukonda | Major | Low |  | 0.15 | 1 |  | 2024-10-24 12:30 |  | Sprint 24.7 |  |  | 2024-10-15 10:37 | 2024-10-24 23:23 |  | 1
14849 | Bug | vManager | MarketPlace | Reported by Nick WIll at Red Bull - he is reporting that when using the Marketplace to buy commodit... | Waiting to be Released | Chandra Kiranmai | Brian McIntyre | Durga Bhavani | Santosh Poloju | Bhanu Anukonda | Bhanu Anukonda | Major |  | Red Bull | 1 | 16 | 2024-10-04 12:30 |  |  | Sprint 24.7 |  |  | 2024-09-27 18:23 | 2024-10-17 17:31 |  | 28
14159 | Enhancement | Expense Management | Managed Pay | Change to Managed Pay Booking Package View | Waiting to be Released | Partha Saradhi Billa | Adam Shawley | Yugandhar Vadisela | Santosh Poloju | Adam Shawley | Adam Shawley | Major |  |  | 8 | 4 | 2024-10-14 12:30 | 2024-10-16 12:30 | 2 | Sprint 24.7 |  |  | 2024-07-24 22:02 | 2024-10-24 22:31 |  | 19 |  | 8
12464 | Enhancement | iPath | Cases | Carrier Escalation Lists in Tickets | Waiting to be Released | Chandra Kiranmai | Josh Kramer | Tejaswi Rontala | Santosh Poloju | Josh Kramer | Katie Terascavage | Major |  |  | 36 | 64 | 2024-10-21 12:30 | 2024-10-22 12:30 |  | Sprint 24.7 |  |  | 2024-02-26 22:39 | 2024-10-24 22:27 |  | 29 |  | 2